{"text_format":"3","workbook":"xls","n_sheets":2,"sheets":["建筑工程","临时工程"],"not_rendered":{"external_links":1,"defined_names":2},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"建筑工程","index":0,"n_rows":98,"n_cols":6,"rows_kept":98,"merged":[[0,0,0,5]],"flags":["formulas_cached_only"]}
["西峡县丹水河七峪村至廖坟村段河道治理工程（一期）--K5+900～K8+713（2标）建筑工程量清单"]
["序号","工程或费用名称","单位","数量","单价(元)","合计(万元)"]
["","第一部分  建筑工程","",{"v":0,"d":"0.00"},0,{"v":0,"d":"0.00"}]
["壹","第一部分  建筑工程","",{"v":0,"d":"0.00"}]
["二","防护工程","",{"v":0,"d":"0.00"}]
["3","K5+900~K6+455左岸格宾石笼护坡","",{"v":0,"d":"0.00"}]
["3.1","清基（机械、Ⅳ类土、弃土运2km）","m3",1638.83]
["3.2","岸坡土方开挖（机械、Ⅳ类土、用于本段回填）","m3",28.27]
["3.3","岸坡土方开挖（机械、Ⅳ类土、附近取土2km用于岸坡土方回填）","m3",{"v":955.3119999999999,"d":"955.31"}]
["3.4","岸坡土方回填（机械、Ⅳ类土料）","m3",{"v":1624.8,"d":"1624.80"}]
["3.5","护脚土方开挖（机械、Ⅳ类土、用于土方回填）","m3",1186.32]
["3.6","护脚土方回填（机械、Ⅳ类土）","m3",{"v":214.1,"d":"214.10"}]
["3.7","格宾石笼护坡（0.3m厚）","m3",1563.44]
["3.8","C25砼压顶（0.3×0.5）","m3",86.69]
["3.9","格宾石笼护脚（0.5m厚）","m3",866.86]
["3.10","撒播草籽护坡","m2",{"v":1178.7799999999997,"d":"1178.78"}]
["3.11","普通标准钢模板","m2",{"v":271.11999999999995,"d":"271.12"}]
["3.12","闭孔低发泡沫塑料板伸缩缝","m2",{"v":275.19999999999993,"d":"275.20"}]
["3.13","反滤土工布（300g/m2）","m2",7118.58]
["3.14","砼护坡拆除弃运2km","m3",490.68]
["3.15","砼护脚拆除弃运2km","m3",288.95]
["4","K5+900~K6+455右岸格宾石笼护坡","",{"v":0,"d":"0.00"}]
["4.1","清基（机械、Ⅳ类土、弃土运2km）","m3",1652.33]
["4.2","岸坡土方开挖（机械、Ⅳ类土、用于本段回填）","m3",{"v":258.21999999999997,"d":"258.22"}]
["4.3","岸坡土方开挖（机械、Ⅳ类土、附近取土2km用于岸坡土方回填）","m3",{"v":1251.1644000000003,"d":"1251.16"}]
["4.4","岸坡土方回填（机械、Ⅳ类土）","m3",{"v":1927.2100000000005,"d":"1927.21"}]
["4.5","护脚土方开挖（机械、Ⅳ类土、用于本段回填）","m3",{"v":1012.9600000000003,"d":"1012.96"}]
["4.6","护脚土方回填（机械、Ⅳ类土）","m3",210.37]
["4.7","格宾石笼护坡（0.3m厚）","m3",{"v":1709.5099999999998,"d":"1709.51"}]
["4.8","C25砼压顶（0.3×0.5）","m3",87.94]
["4.9","格宾石笼护脚（0.5m厚）","m3",{"v":879.3999999999999,"d":"879.40"}]
["4.10","普通标准钢模板","m2",{"v":315.09000000000003,"d":"315.09"}]
["4.11","闭孔低发泡沫塑料板伸缩缝","m2",320.78]
["4.12","反滤土工布（300g/m2）","m2",7310.98]
["4.13","砼护坡拆除弃运2km","m3",593.95]
["4.14","砼护脚拆除弃运2km","m3",{"v":293.14000000000004,"d":"293.14"}]
["5","K6+783~K6+948右岸格宾石笼护坡","",{"v":0,"d":"0.00"}]
["5.1","清基（机械、Ⅳ类土、弃土运3km）","m3",703.75]
["5.2","岸坡土方开挖（机械、Ⅳ类土、用于本段回填）","m3",79.64]
["5.3","岸坡土方开挖（机械、Ⅳ类土、附近取土3km用于岸坡土方回填）","m3",1217.36]
["5.4","岸坡土方回填（机械、Ⅳ类土）","m3",{"v":1382.4,"d":"1382.40"}]
["5.5","护脚土方开挖（机械、Ⅳ类土、用于本段回填）","m3",401.65]
["5.6","护脚土方回填（机械、Ⅳ类土）","m3",57.13]
["5.7","格宾石笼护坡（0.3m厚）","m3",620.66]
["5.8","C25砼压顶（0.3×0.5）","m3",25.79]
["5.9","格宾石笼护脚（0.5m厚）","m3",257.89]
["5.10","普通标准钢模板","m2",92.41]
["5.11","闭孔低发泡沫塑料板伸缩缝","m2",21.49]
["5.12","反滤土工布（300g/m2）","m2",2636.21]
["5.13","砼护坡拆除弃运3km","m3",314.84]
["5.14","砼护脚拆除弃运3km","m3",85.96]
["6","K6+960~K7+365右岸格宾石笼护坡","",{"v":0,"d":"0.00"}]
["6.1","清基（机械、Ⅳ类土、弃土运4km）","m3",1462.08]
["6.2","岸坡土方开挖（机械、Ⅳ类土、用于本段回填）","m3",62.32]
["6.3","岸坡土方开挖（机械、Ⅳ类土、附近取土4km用于岸坡土方回填）","m3",436.04]
["6.4","岸坡土方回填（机械、Ⅳ类土）","m3",986.68]
["6.5","护脚土方开挖（机械、Ⅳ类土、用于本段回填）","m3",873.74]
["6.6","护脚土方回填（机械、Ⅳ类土）","m3",176.12]
["6.7","格宾石笼护坡（0.3m厚）","m3",1350.64]
["6.8","C25砼压顶（0.3×0.5）","m3",85.55]
["6.9","格宾石笼护脚（0.5m厚）","m3",611.04]
["6.10","普通标准钢模板","m2",306.54]
["6.11","闭孔低发泡沫塑料板伸缩缝","m2",50.92]
["6.12","反滤土工布（300g/m2）","m2",5910.09]
["6.13","砼护坡拆除弃运4km","m3",591.57]
["6.14","砼护脚拆除弃运4km","m3",203.68]
["6.15","砼路面拆除弃运4km","m3",36.66]
["6.16","C25砼路面恢复（厚0.18m）","m2",203.68]
["6.17","碎石垫层（厚0.1m）","m3",20.37]
["6.18","汉白玉栏杆（柱高1.2m，板厚0.1m，高1m）","m",{"v":408,"d":"408.00"}]
["7","K8+216-K8+713右岸格宾石笼护坡","",{"v":0,"d":"0.00"}]
["7.1","清基（机械、Ⅳ类土、弃土运4km）","m3",1591.81]
["7.2","岸坡土方开挖（机械、Ⅳ类土、用于本段回填）","m3",69.06]
["7.3","岸坡土方开挖（机械、Ⅳ类土、附近取土4km用于岸坡土方回填）","m3",1620.92]
["7.4","岸坡土方回填（机械、Ⅳ类土）","m3",2217.56]
["7.5","护脚土方开挖（机械、Ⅳ类土、用于本段回填）","m3",1117.89]
["7.6","护脚土方回填（机械、Ⅳ类土）","m3",161.99]
["7.7","格宾石笼护坡（0.3m厚）","m3",1578.82]
["7.8","C25砼压顶（0.3×0.5）","m3",80.42]
["7.9","格宾石笼护脚（0.5m厚）","m3",{"v":804.2,"d":"804.20"}]
["7.10","撒播草籽护坡","m2",323.22]
["7.11","普通标准钢模板","m2",288.17]
["7.12","闭孔低发泡沫塑料板伸缩缝","m2",307.87]
["7.13","反滤土工布（300g/m2）","m2",7030.45]
["7.14","砼护坡拆除弃运4km","m3",551.45]
["7.15","砼护脚拆除弃运4km","m3",268.07]
["8","K6+719~K6+783右岸C25砼挡墙","",{"v":0,"d":"0.00"}]
["8.1","岸坡土方开挖（机械、Ⅳ类土、用于本段回填）","m3",667.88]
["8.2","岸坡土方开挖（机械、Ⅳ类土、弃土运3km）","m3",437.18]
["8.3","岸坡土方回填（机械、Ⅳ类土）","m3",566.51]
["8.4","M10浆砌石挡墙（顶宽0.5m)","m3",377.15]
["8.5","普通标准钢模板","m2",568.76]
["8.6","闭孔低发泡沫塑料板伸缩缝","m2",50.42]
["8.7","DN50PVC排水管","m",50.18]
["8.8","格宾石笼护脚（0.5m厚）","m3",{"v":130.725,"d":"130.73"}]
["8.9","M10浆砌石扭面护坡","m3",{"v":15,"d":"15.00"}]
["8.10","砼护坡拆除弃运2km","m3",581.07]
["8.11","砼护脚拆除弃运2km","m3",31.96]

{"sheet":"临时工程","index":1,"n_rows":8,"n_cols":6,"rows_kept":8,"merged":[[0,0,0,5]],"flags":["formulas_cached_only"]}
["西峡县丹水河七峪村至廖坟村段河道治理工程（一期）--K5+900～K8+713（2标）临时工程量清单"]
["序号","工程或费用名称","单位","数量","单价(元)","合计(万元)"]
["","第四部分  施工临时工程","",0,0,{"v":0,"d":"0.00"}]
["肆","第四部分  施工临时工程","",0]
["四","施工房屋建筑工程","",0]
["1","施工仓库","m2",100]
["2","办公、生活及文化福利建筑","%",1.5,"单价为以上费用之和 "]
["五","其他临时工程","%",1,"单价为以上费用之和 "]